## Sheet1
STATERA ENERGY LTD - CLIFFE SEISMIC SURVEY - CONTACTS SCHEDULE |  |  | Ver: 26/08/22
ORGANISATION/BODY | POINT OF CONTACT DETAILS | TEL No | COMMENTS/REQUIREMENTS
NATURAL ENGLAND | ProtectedSites@naturalengland.org.uk |  | For Port of London Authority Owned Land.
Being a Statutory Authority the PLA will need to submit
an Assent Advice Request to NE for works agreement
covering the land within/adjacent to the S Thames Estuary
and Marshes SSSI/RAMSAR/SPA area. Confirmation is still
required whether Mucking Flatts is part of the Authority
ownership.
NE has 28 days to respond.
Cost involved - £500.00 per adviser for 90 min meeting
then £110.00 per additional hr.
As part of the Authority ownership is classified as RAMSAR
and SPA, a HABITAT REGULATIONS ASSESSMENT is required
and should be included with the Assent request.
(Suggest the HRA above covers the entire survey area)
For Non Statutory Owner/Occupier Land.
A standard Notice of Proposal to Cause, Carry Out Or
Permit Operations should be submitted by the
Owner/Occupier.
HISTORIC ENGLAND | customers@HistoricEngland.org.uk | 0370 3330607 | Specific to the Cliffe Explosive Works SAM where survey
access can't be avoided, an application for Scheduled
Monument Consent is required. Line plan and survey
methodology will need to be included. There appears to be
5 other SAMs falling within the survey area. Should any
theoretical line routing fall within any of these, it is
suggested line positioning is adjusted to avoid these.
STATERA ENERGY LTD - CLIFFE SEISMIC SURVEY - CONTACTS SCHEDULE
ORGANISATION/BODY | POINT OF CONTACT DETAILS | TEL No | COMMENTS/REQUIREMENTS
SOUTHERN WATER |  | 0800 085 8060 | Digdat has confirmed plans can only be provided via
c/o Digdat for |  |  | creating an account on their website and downloading
Clean Water & Sewers |  |  | them direct. They can't provide paper or electronic detail
themselves.
Cost involved but this will be wavered subject to the PLA
confirming in writing that they are involved in the survey
and are a Statutory Authority.
ESSEX & SUFFOLK WATER | plans@nwl.co.uk |  | For Thurrock
NATIONAL GRID | AssetProtection@nationalgrid.com | 01926 654844 | Two HP Gas pipeline routes affected north and south of
For National Transmission Gas |  |  | the River Thames.
& Electricity |  |  | Initial search undertaken via 'Line Search Before You Dig'
SGN SOUTH EASTERN | plantlocation@sgn.co.uk | 0800 9121722 | Initial search undertaken via 'Line Search Before You Dig'
For Gas south of R Thames
CADENT | plantprotection@cadentgas.com | 0800 688588 | Initial search undertaken via 'Line Search Before You Dig'
For Gas north of R Thames
UK POWER NETWORKS | Plant Provision: Martin Johnson | 0800 056 5866 | On receipt of survey line plan, will calculate cost for
Electricity Assets | plans@ukpowernetworks.co.uk |  | provision of details. Still to confirm whether payment will
be applicable on receipt of PLA Statutory Authority
confirmation letter.
VODAFONE | Contact via:
(Fibre Optics) | osm.enquiries@atkinsglobal.com
STATERA ENERGY LTD - CLIFFE SEISMIC SURVEY - CONTACTS SCHEDULE
ORGANISATION/BODY | POINT OF CONTACT DETAILS | TEL No | COMMENTS/REQUIREMENTS
KENT COUNTY COUNCIL | Sharon Thompson | 03000 413468 | For area south of R Thames centred on Church Street,
For GPDO Notification | Planning, Development, Environment & |  | Borough of Gravesham.
Planning Policy Manager
Growth & Communities, KCC, Invicta Hse,
County Hall, Maidstone, ME14 1XX
sharon.thompson@kent.gov.uk
For Heritage | Search via:
webapps.kent.gov.uk
MEDWAY COUNCIL | Dave Harris | 01634 331575 | For area south of R Thames centred on Cliffe.
(Unitary Authority) | Head of Planning, Medway Council, Gun
For GPDO Notification | Wharf, Dock Road, Chatham, Kent,
ME4 4TR
dave.harris@medway.gov.uk
THURROCK COUNCIL | Leigh Nicholson | 01375 652652 | For area north of R Thames centred on East Tilbury.
(Unitary Authority) | Assistant Director, Planning, Transport & | (Not Direct)
For GPDO Notification | Public Protection, Civic Offices, New Rd,
Greys, RM17 6SL
development.management@thurrock.gov.uk
For Heritage - Listed Buildings, | Search via Planning Constraints Map:
Conservation Areas | thurrock.maps.arcgis.com
GRAVESHAM BOROUGH COUNCIL | Civic Centre, Gravesham, Kent,
Planning Dept | DA12 1AU
planning.consultation@gravesham.gov.uk
SHORNE PARISH COUNCIL | Sarah Poole, c/o Shorne Village Hall, | 01634 243157 | Kent
Clerk to the Council | The Street, Shorne, Gravesend, Kent,
DA12 3EA
clerk@shorneparishcouncil.org
STATERA ENERGY LTD - CLIFFE SEISMIC SURVEY - CONTACTS SCHEDULE
ORGANISATION/BODY | POINT OF CONTACT DETAILS | TEL No | COMMENTS/REQUIREMENTS
HIGHAM Parish Council | Mrs Linda Atkinson, 32 Goodwood Close, |  | Kent
Clerk to the Council | High Halstow, Kent, ME3 8SU
clerk@higham-kent-pc.gov.uk
CLIFFE & CLIFFE WOODS | Mr Chris Fribbins, 42 Quickrells Avenue, |  | Medway
PARISH COUNCIL | Cliffe, Rochester, Kent, ME3 7RB
Clerk to the Council | clerk@cliffeandcliffewoods-pc.gov.uk
COOLING PARISH COUNCIL | Melanie Wright, Manor House, Lower |  | Medway
Clerk to the Council | Twydall Lane, Gillingham, Kent, ME7 2UX
info@coolingparishcouncil.org
(NO Parish Councils within
THURROCK)
ENVIRONMENT AGENCY | National Customer Contact Centre, | 03708 506506
PO Box 544, Rotherham, S60 1BY
enquiries@environment-agency.gov.uk
NTH KENT MARSHES IDB | c/o Lower Medway IDB, 13 Conqueror | 01795 468000
enquiries@lmidb.co.uk
RSPB | Salt Lane, Rochester, ME3 7SX | 01634 222480 | Area Manager for Kent & Essex: Alan Johnson
For Cliffe Pools Nature Reserve | northkentmarshes@rspb.org.uk
KENT WILDLIFE TRUST | Tyland Barn, Chatham Road, Sanling, | 01622 662012 | Covers Medway
Maidstone, ME14 3BD
info@kentwildlife.org.uk
STATERA ENERGY LTD - CLIFFE SEISMIC SURVEY - CONTACTS SCHEDULE
ORGANISATION/BODY | POINT OF CONTACT DETAILS | TEL No | COMMENTS/REQUIREMENTS
ESSEX WILDLIFE TRUST | Abbotts Hall Farm Maldon Road, | 01621 862960 | Covers Thurrock
Gt Wigborough, Colchester, CO5 7RZ
enquiries@essexwt.org.uk
MARINE MANAGEMENT | Lancaster House, Hampshire Court, | 03001 231032 | River Thames falls within the MMO South East Inshore
ORGANISATION | Newcastle upon Tyne, NE4 7YH | (General Enquiries) | Area - Marine contractor to advise if necessary
KENT POLICE | Contact via their website |  | Covers Medway area
For Firearms & Explosives
ESSEX POLICE | Contact via their website |  | Covers Thurrock area
For Firearms & Explosives